News Release

FOR IMMEDIATE RELEASE 					CONTACT: Brian Smith

June 13, 2023 							    Maintenance Section Supervisor

(301) 600-1565

Road Closures Scheduled on Bethel Road

FREDERICK, Md – Starting on or about June 26 through August 11, several road closures are scheduled on Bethel Road for stormwater pipe and headwall replacement.

The project will be divided into four phases, with a total of 22 storm culverts being replaced. A detour route will be in place for each phase at specific locations.

Phase 1

Starting June 26, through July 7, the intersection of Fish Hatchery Road to the intersection of Mountaindale Road will be closed at:

- Site 1 – at Fish Hatchery Road

- Site 2 – 10808 Bethel Road

- Site 3 – 10724 Bethel Road

- Site 4 – 10722 Bethel Road

- Site 5 – 10604 Bethel Road

- Site 6 – 10522 Bethel Road

Phase 2

From approximately July 10 through July 21, the intersection of Yellow Springs Road to the intersection of Ford Road will be closed at specific locations.

Phase 3

From approximately July 24 through August 2 the intersection of Mountaindale Road to the intersection to Willis Lane will be closed at specific locations.

Phase 4

From approximately August 2 through August 11 the intersection of Opossumtown Pike/Putman Road to the intersection of Ford Road will be closed at specific locations.

Closure dates may vary due to weather conditions and updates will be provided as the project progresses. For further information, contact, Brian Smith, Maintenance Section Supervisor via email using BSmith4@frederickcountymd.gov.

###